## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
1 | Check the user level | As an administrator I want to see all of the existing customer hierarchy so that I can determine if the current level architectures are reasonable | very high | 1 | The customer hierarchy needs to represent all existing levels and the names of each level The customer hierarchy needs to be presented in the form of a hierarchy tree The customer hierarchy needs to be displayed in the middle of the interface and can be clearly displayed Make sure that the latest customer hierarchy shown is up to date |  | 3.29 | 4.9
2 | Display of Member Benefits | As a non-member I want to know all the rights and interests that members have so that I can decide whether joining the membership or not | very high | 1 | A membership rights text should be displayed in the membership panel |  | 3.29 | 4.9
3 | Selecting Category | As a member of gym I want to select the videos of particular category So that I can find the videos I want effectively | very high | 1 | Verify that the category list is shown in the video search page for the customer to choose Verify that videos of that particular category can be automatically shown once the customer choose a category Verify that videos will be listed in a default order (eg. Chronologically) for the customer to look through |  | 3.29 | 4.9
4 | Keyword Searching | As a end-user I want to search the videos by key words So that I can screen out the videos I care about | very high | 1 | Verify that there is a search bar in the video page for the users to type in words. Verify that the relevant videos will be shown to the end-users once the user press “Search” button. |  | 3.29 | 4.9
5 | Check the customer’s name | As an administrator I want to look up users by name or ID so that I can issue benefits to a specific user | high | 2 | Make sure the customer the system finds is a member The name and ID can be queried in conjunction with other options as a filter criteria |  | 4.12 | 4.23
6 | Check the customer’s level | As an administrator I want to look up users based on a specific level so that I can issue different benefits to different levels of customers | medium | 2 | Multiple levels can be selected to query simultaneously The customer level can be queried in conjunction with other options as a filter criteria |  | 4.12 | 4.23
7 | Check the customer’s gender and issue benefits | As an administrator I want to look up users based on a given gender so I can issue benefits to all users of a certain gender on a special day | medium | 2 | The gender can be queried in conjunction with other options as a filter criteria |  | 4.12 | 4.23
8 | Sort the search result | As an administrator I want to sort the result by different standard so that I can easily find the result I'm interested. | high | 2 | The system can sort the result by cliking some button and show the sorted result quickly |  | 4.12 | 4.23
9 | Modify the information of customer | As an administrator I want to modify the information fo customer so that I can correct something wrong if any | high | 2 | The system will provide a table so that the administrator can modify the text |  | 4.12 | 4.23
10 | Check my own membership level | As a member I want to be able to easily see my membership levels so that I can see what benefits are available to me | high | 2 | The membership level should be prominently displayed at the top of the screen |  | 4.12 | 4.23
11 | View the remaining membership time | As a member I want to easily see my remaining membership time so that I can know when I need to top up next time and when my membership benefits expire | high | 2 | Membership time remaining should be displayed next to the membership level |  | 4.12 | 4.23
12 | View membership rewards points | As a member I want to easily see my membership rewards points so that I can know how many points I have available | high | 2 | membership rewards points should be prominently displayed below the membership level Use a progress bar to display the current membership rewards points and the points required to reach the next level. |  | 4.12 | 4.23
13 | Sort the video result | As a member I want to sort the video search result by viewcount, like, etc. so that I can find the things I'm interested easily | high | 2 | The system can sort the result by cliking some button and show the sorted result quickly |  | 4.12 | 4.23
14 | Sort the live session search result | As a member I want to sort the live session search result so that I can find the result easily | high | 2 | The system can sort the result by cliking some button and show the sorted result quickly |  | 4.12 | 4.23
15 | Contact Panel | As a member I want to submit some advice to the gym so that I can help the gym do better | high | 3 | There should be a panel to input email, subject and content. Once the user click "submit", the gym will receive this message. |  | 4.12 | 4.23
16 | Adding Videos | As an administrator I want to add videos to the platform provided for customers So that I can enrich the content of the software for the customers to enjoy | high | 3 | Verify that videos can be uploaded directly by the administrator through selecting files of operating system such as OS X, Windows Verify that the video overview picture can be randomly generated Verify that the administrator can fill in a table to complete the information of the video while uploading the video. |  | 4.26 | 5.14
17 | Modification of videos | As an administrator I want to modify the information of videos So that I can correct the information which is typed wrong before | high | 3 | Verify that there is a ‘gear’ icon for the administrator to press so that the administrator can enter the information modification page. |  | 4.26 | 5.14
18 | Rating | As a customer I want to rate the videos So that I can recommend my preferred videos to all the other users of this software | medium | 3 | Customer can rate a video by score from 1 to 10 once after he/she watches the video. All the scores from a wide range of customers will be used to generate the overall rating score for one video The rating score of a video will be shown under the video. |  | 4.26 | 5.14
19 | Favourite list | As a end-user I want to add some videos to my favourite list So that I can find them again easily when I want to watch them again, especially when I forget their titles. | medium | 3 | Verify that there is a star icon for the user to press so that the video can be added to the user’s favourite list Verify that the user can enter the favourite list in their personal page |  | 4.26 | 5.14
20 | likes | As a end-user I want to give likes to some videos So that I can encourage the video producer | medium | 3 | Verify that there is a thumb icon in the video page for users to choose. Verify that the number of likes can be shown in the video page. |  | 4.26 | 5.14
21 | history record | As a end-user I want to have a history record which keeps the videos that I’ve watched before So that I can look back to them later | medium | 3 | Verify that the system can record every browsing track of the user Verify that the browsing history can be found in the personal page. |  | 4.26 | 5.14
22 | add the live session to class list | As a gym premier member I want to add the live sessions that I have booked to my own class list. So that I can directly attend it every time I log in and enter personal home page | medium | 3 | Verify the customer can add the live sessions into their class list. Verify after adding, the class list of customers can change timely. Verify the customer can check the class list in the home page. |  | 4.26 | 5.14
23 | Book the live session | As a gym premier member I want to booked the live session that I have selected. So that I can attend the corresponding lecture | high | 3 | Verify the customer can see which classes can be choosn. Verify the customer can book the live session and can receive notification if booked successfully. |  | 4.26 | 5.14
24 | Membership expiration reminder | As a member I want to receive a timely reminder before the expiration of my membership so that I can keep my membership | high | 3 | An alert trigger should be displayed on the top of the user interface within three days remained |  | 4.26 | 5.14
25 | Open account | As an administrator I want to get the customer's nickname, password, email, gender, and date of birth when they register their account so that I can open an account for a new customer and enter the account information into the system | high | 3 | Verify that the customer does not exist in system The customer's height and weight information can be entered as optional information |  | 4.26 | 5.14
26 | search the live session based on personal plan | As a gym premier member I want to filter the live sessions based on my personal plan. For example, I can only attend the Yoga classes or strength classes. So that I can get more targeted training | medium | 3 | Verify the premier member can filter the live sessions based on their personal plan. |  | 4.26 | 5.14
27 | Monthly income | As an administrator I want to see the monthly income of the membership fee so that I can assess how profitable our gym is | low | 4 | The bar chart shows the monthly income of membership fees in the past 12 months and the annual income of membership fees in the past three years |  | 5.17 | 5.21
28 | Commenting | As a customer I want to comment on the videos So that I can share my ideas with other users, even I can make friends with them through the communication in the comment area. | medium | 4 | Verify that the user can type in the text filed under the video to send comment Verify that the text encoding of the comment support UTF-8, in other words, Chinese, English, Japanese and other languages all over the world will be supported. Verify that the user can see the comments sent by other users. |  | 5.17 | 5.21
29 | Birthday discount | As a member I want to get extra discounts on my birthday so that I would be more willing to become a member | medium | 4 | - Make sure that only members can view such courses |  | 5.17 | 5.21
30 | Exclusive live and recorded broadcasting | As a member I want to have live sports courses and action instructions recorded by coaches exclusively for members so that I can enjoy better exercise guidance after becoming a member | very low | 5 | Members-only courses need to be presented uniformly in a specific interface |  | 5.24 | 5.28
31 | Hottest Video | As a professional trainer I want to know the hottest video in the recent days So that I can catch up with the trend | very low | 5 | Verify the watching history of one particular video can be recorded in the files. Verify the software can work out the hottest video in terms of the viewing times. Verify the hottest video can be shown in the main page or search page |  | 5.24 | 5.28
32 | add categories | As an administrator I want to add categories of training video to the software So that I can introduce a new way of training to my users | high | 5 | Verify that the administrator can add new category in the management page Verify that the newly added category can be searched by the end-users. |  | 5.24 | 5.28